## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Krish Desai
Document Created On: | 2024-06-26
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Career Analytics with Python |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Career Analytics with Python(Project Schedule)
PROJECT SCOPE
PROJECT START DATE | 2024-06-05
PROJECT END DATE | 2024-07-25
OVERALL PROGRESS | COMPLETED
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem | Krish Desai | 2024-06-12 | 2024-06-13 | 2 | COMPLETED
| 1.2 Createa a project charter | Krish Desai | 2024-06-15 | 2024-06-18 | 3 | COMPLETED
| 1.3 Create a SRS document | Krish Desai | 2024-06-19 | 2024-06-20 | 2 | COMPLETED
| 1.4 Requirement gathering | Krish Desai | 2024-06-21 | 2024-06-22 | 3 | COMPLETED
2 Planning
| 2.1 Create WBS | Krish Desai | 2024-06-24 | 2024-06-25 | 2 | COMPLETED
| 2.2 Baseline project plan | Krish Desai | 2024-06-26 | 2024-06-27 | 2 | COMPLETED
| 2.3 RAID logs | Krish Desai | 2024-06-29 | 2024-06-30 | 2 | COMPLETED
3 Execution
| Data Cleaning | Krish Desai | 2024-07-06 | 2024-07-07 | 2 | COMPLETED
| Feature engineering | Krish Desai | 2024-07-09 | 2024-07-10 | 2 | COMPLETED
| Solving Problem Statement | Krish Desai | 2024-07-12 | 2024-07-17 | 6 | COMPLETED
| Visualisation | Krish Desai | 2024-07-18 | 2024-07-19 | 2 | COMPLETED
| Presentation video | Krish Desai | 2024-07-22 | 2024-07-22 | 1 | COMPLETED
| Lessons learnt | Krish Desai | 2024-07-23 | 2024-07-23 | 1 | COMPLETED
3.3 Report
| 3.3.1 Generate Project Report | Krish Desai | 2024-07-23 | 2024-07-24 | 2 | COMPLETED
| 4 Closure | Krish Desai | 2024-07-25 | 2024-07-25 | 1 | COMPLETED